## Slide 1
PROJECT OVERVIEW
ShiftPay
Shift logging, compensatory-off entitlement and pay computation, delivered as a scoped ServiceNow application.
100
work items on the board
83
delivered and closed
7
two-week sprints
6
people across six disciplines
What it does
— An employee logs one shift per day, sees what a compound on-call shift entitles them to, and submits the month for approval.
— A manager reviews a reportee's month, corrects a single day with a recorded reason, and approves or rejects singly or in bulk.
— Pay is aggregated weekly and monthly against a rate captured at compute time, so a later rate change cannot rewrite history.
— A read-only Power BI layer reports over the same tables and reimplements no shift or pay rule.
Team
Geetha Nallamada · Sr Data Analyst
Requirements, reporting design, sign-off
Shashank Shukla · IT Consultant
Platform, Script Includes, deployment
Rucha Joshi · UI Developer
Service Portal widgets
Divya Maram · Data Analyst
Data model, catalogue semantics, measures
Neha Chauhan · QA Analyst
Test pack and evidence records
Swopneel · SDET
Harness, CI and contract tests
ShiftPay · ServiceNow scoped application · status as at 3 September 2026
1

## Slide 2
HOW THE WORK WAS SEQUENCED
Delivery plan
A pre-build phase from 1 May, then seven two-week sprints to 11 September 2026. Scope was fixed at each boundary and nothing was closed to flatter the board.
Pre-build
01–29 May
Test engineering first: harness, nightly pipeline, contract tests
Complete
Sprint 1
08–19 Jun
Foundations: requirements signed off, landing page, month grid
Complete
Sprint 2
22 Jun–03 Jul
Day writes, bulk apply, data-driven catalogue semantics
Complete
Sprint 3
06–17 Jul
Shared rule layer extracted, month lock, deployment path
Complete
Sprint 4
20–31 Jul
Manager approval queue, calendar rules, test harness
Complete
Sprint 5
03–14 Aug
Day correction with audit, Power BI model, evidence generator
Complete
Sprint 6
17–28 Aug
History tab, money guard, reporting pages, metadata sweep
Complete
Sprint 7
31 Aug–11 Sep
Instance retarget, generated documents, handover
In progress
Pre-build and six sprints complete · sprint 7 closes 11 September with the handover session
ShiftPay · ServiceNow scoped application · status as at 3 September 2026
2

## Slide 3
WHAT HAS BEEN BUILT
Deliverables
Three widgets over one shared rule layer, with a reporting layer and a test pack that both read the same data and reimplement none of the rules.
Service Portal widgets
— Employee calendar — log a day, see CO entitlement, submit and lock a month
— Manager approvals — queue, bulk actions, day correction with audit, history
— Landing page — entry point for both journeys
Shared rule layer
— Aggregator — weekly and monthly pay against a rate snapshot
— Entitlements — compensatory-off lifecycle over a seven-weekday window
— Calendar rules — catalogue, holidays, which shifts a user may log
Reporting and assurance
— Power BI — read-only, money from the snapshot, never live rates
— Test pack — harness and CI from May, 40 cases, 9 automated, Word evidence
— Documents — requirements, technical design, test cases, setup runbook
Two rules the delivery holds to
Money is read from the summary snapshot and never from live catalogue rates · shift meaning lives in catalogue columns keyed by sys_id, so renaming a shift type changes no behaviour
ShiftPay · ServiceNow scoped application · status as at 3 September 2026
3

## Slide 4
WHAT REMAINS
Roadmap
83 of 100 items closed. 4 defects stay open deliberately — the test pack is expected to fail on them, and a fully green run would mean the assertions had broken.
Now — in flight
— SP-58 weekend catalogue fix, prepared and awaiting a verified re-run
— SP-57 P1: server refusals invisible, calendar repaints as success
— SP-59 · SP-60 · SP-61 open findings held on the board, not hidden
Next — to 11 Sep
— Close the P1 and re-run the pack to confirm the case turns green
— SP-76 handover session: widget contract, rule layer, deployment traps
— Final document regeneration from source for the handover pack
Later — phase two
— Approval audit table so a resubmission cannot erase a rejection
— Table ACLs, payroll export, scheduled dataset refresh
— Half-day support and responsive calendar — needs a requirements change
Decision needed from the sponsor
Table ACLs were scoped out of the proof of concept by agreement. Production use needs them written, and the widget-level guards that stand in for them today must stay rigorous either way.
ShiftPay · ServiceNow scoped application · status as at 3 September 2026
4